Blue Ridge

Festival of Bands

Operations Guide

Contents

Purpose	4

Audience	4

Timeline Overview	4

Phase 1: Strategic Planning & Foundation (2-3 Months Prior to BRFB)	5

1.	Confirm Event Date and Time:	5

2.	Establish BRFB Planning Committee & Define Key Roles:	5

3.	Develop Initial Budget & Set Financial Goals:	5

4.	Identify and Secure Event Sponsors:	6

5.	Invitations & Registration for Visiting Bands:	6

Phase 2: Operational Development (1-2 Months Prior to BRFB)	7

1.	Prepare Visiting Band Information Packets (Initial Draft):	7

2.	Secure Food and Merchandise Vendors & Plan Concessions Strategy:	7

4.	Secure Judges & Adjudication Panel:	8

5.	Develop Event Logistics & Site Plan:	8

6.	Develop Marketing & Promotion Plan:	9

Phase 3: Final Preparations & Logistics (2-4 Weeks Prior to BRFB)	10

1.	Finalize Volunteer Roster & Create Detailed Schedule:	10

2.	Conduct Volunteer Training & Briefing Sessions:	10

3.	Finalize Arrangements with Food/Merchandise Vendors & Concessions Plan:	11

4.	Competition Program: Planning, Development & Publication	11

5.	Order/Prepare Trophies & Awards:	14

6.	Assemble Visiting Band Information Packets (Final Version):	14

8.	Prepare Event Signage:	14

9.	Equipment & Supplies Procurement/Check:	15

Phase 4: Event Week Mobilization (1 Week to 1 Day Prior to BRFB)	17

1.	Final Venue Walk-Through:	17

2.	Confirm Volunteer Shifts & Send Reminders:	17

3.	Prepare Cash Boxes & Payment Systems:	17

4.	Final Communications:	17

5.	Set Up "Day Of" Command Center Plan:	18

Phase 5: BRFB Event Day Execution	19

1.	Early Morning: Setup & Volunteer Check-in:	19

2.	Vendor & Band Arrival/Registration:	19

3.	Managing Event Flow:	19

4.	Hospitality:	20

5.	Troubleshooting & Issue Resolution:	20

6.	Awards Ceremony:	20

Phase 6: Post-Event Wrap-Up & Review (1 Day to 1 Week After BRFB)	21

1.	Immediate Post-Event: Venue Cleanup & Teardown:	21

2.	Financial Reconciliation (Next Business Day):	21

3.	Send Performance Recordings to Visiting Band Directors:	21

4.	Distribute Thank You Communications:	21

5.	Celebrate Success & Share Results (Social Media & Community):	22

6.	Post-Event Review Meeting & Documentation:	22

7.	Final Financial Reporting:	22

Purpose

This guide provides a comprehensive framework for the planning, execution, and post-event activities related to the annual Blue Ridge Festival of Bands. Its aim is to ensure consistency, efficiency, and success in hosting this vital fundraiser for the William Byrd High School music program.

Audience

This guide is intended for BRFB Committee Chairs, Band Booster members, and key volunteers involved in the festival's operations.

Timeline Overview

Phase 1: Strategic Planning & Foundation (2-3 Months Prior)

Phase 2: Operational Development (1-2 Months Prior)

Phase 3: Final Preparations & Logistics (2-4 Weeks Prior)

Phase 4: Event Week Mobilization (1 Week Prior)

Phase 5: BRFB Event Day Execution

Phase 6: Post-Event Wrap-Up & Review (1 Day to 1 Week After)

Phase 1: Strategic Planning & Foundation (2-3 Months Prior to BRFB)

This initial phase focuses on establishing the core elements and securing essential commitments for the festival.

- Confirm Event Date and Time:

- Action: Liaise with school administration and district officials to secure the primary date, and necessary facilities (stadium, parking, indoor spaces for warm-ups, judges' hospitality, etc.).

- Responsible: Director

- Key Consideration: Ensure no major conflicts with other school, district, or significant community events.

- Establish BRFB Planning Committee & Define Key Roles:

- Action: Recruit and confirm leads for critical areas (e.g., Chairperson, Treasurer/Finance, Sponsorship Coordinator, Band Liaison, Food & Concessions, Volunteers, Logistics/Operations, Publicity/Marketing, Awards/Trophies).

- Responsible: Executive Board

- Output: A documented list of committee members and their specific responsibilities. Schedule regular planning meetings as needed.

- Develop Initial Budget & Set Financial Goals:

- Action: Review previous years' financials. Project anticipated expenses (judges, trophies, sanitation, supplies, etc.) and potential revenue streams (entry fees, sponsorships, concessions, ticket sales, merchandise).

- Responsible: Executive Board

- Key Consideration: Set clear fundraising targets for the event.

- Identify and Secure Event Sponsors:

- Action: Develop sponsorship packages with varying levels and benefits. Begin outreach to previous sponsors and identify new potential local businesses and community organizations.

- Responsible: Ways & Means

- Tool: Sponsorship Form. Review annually for relevance and update as needed. Track outreach and commitments.

- Key Consideration: Ensure sponsor benefits (e.g., program ads, banner placement, announcements) are clearly defined and deliverable.

- Invitations & Registration for Visiting Bands:

- Action: Prepare and distribute invitations to regional high school band directors. Include event details, entry fees, judging criteria (if available), and registration deadlines.

- Responsible: Director

- Current Tool: Outlook/email. Promote the use of the online registration system if possible, for efficiency (e.g., Google Forms, dedicated band competition software).

- Key Consideration: Consult with the Treasurer to establish a clear process for receiving registrations and payments.

Phase 2: Operational Development (1-2 Months Prior to BRFB)

This phase involves fleshing out the operational details and securing necessary resources.

- Prepare Visiting Band Information Packets (Initial Draft):

- Action: Begin compiling essential information for participating bands, including:

  - Festival schedule (preliminary)

  - Map of the venue (parking, warm-up areas, stadium entrance/exit, concessions, restrooms)

  - Emergency contact information

  - Rules and regulations for the event, including the RCPS Clear Bag Policy for stadium entry

- Responsible: Director

- Key Consideration: This will be a living document, updated as more details are finalized.

- Secure Food and Merchandise Vendors & Plan Concessions Strategy:

- Action:

  - Develop the overall concessions strategy, determining the mix of items to be sold by outside vendors versus the Band Boosters.

  - Identify, vet, and secure agreements with external food and merchandise vendors. Ensure no two vendors sell the same primary food items to prevent unfair competition.

  - Liaise with the WBHS Football Boosters to formally reserve the concession stand. During this coordination, conduct a pre-event inventory review and document any special instructions for the use of their space and equipment.

  - Develop the initial menu, product list, and supply needs for all Booster-run concessions, including items for the hospitality area.

- Responsible: Ways & Means, Volunteer Coordinator

- Key Considerations

  - Negotiate and finalize all terms with vendors, including any revenue sharing, and communicate these details to the Treasurer.

  - Begin planning for volunteer staffing needs, preliminary supply lists, and cash handling procedures for Booster-run sales.

  - Review past event data (e.g., prior Sign-Up Genius lists) for detailed information on food types, quantities, volunteer roles, and purchasing information to inform current year planning.

- Posting the Colors (Raising the Flag):

- Action: Invite and confirm the availability of JROTC cadets to present the colors (the American flag) during the playing of the National Anthem. Cadets will also post the colors (mount and raise the flag) on the stadium flagpole.

- Responsible: Director, Volunteer Coordinator

- Key Consideration: Cadets should not be required to stay for the duration of the event, however, a volunteer should be designated at the end of the event to retire the colors (lower and remove the flag), including folding and returning them to their storage area in the concession stand.

- Secure Judges & Adjudication Panel:

- Action: Invite and confirm qualified judges for all categories (e.g., music performance, visual performance, general effect, percussion, color guard).

- Responsible: Director

- Key Consideration: Finalize contracts and hospitality needs for judges. Obtain judge biographies for the event program.

- Develop Event Logistics & Site Plan:

- Action: Create a detailed site plan indicating:

  - Band parking (buses, equipment trucks)

  - Spectator parking

  - Warm-up zones (percussion, woodwinds, full band)

  - Stadium entry/exit flow for bands and spectators

  - First aid station location

  - Vendor placement

  - Restroom facilities

  - Lost and Found

- Responsible: Vice President

- Key Consideration: Liaise with local law enforcement/EMS as needed for onsite coverage during the event.

- Develop Marketing & Promotion Plan:

- Action: Outline strategies to promote the BRFB to the community. This includes:

  - Social media campaign (Facebook)

  - Website updates

  - School newsletters (Middle & High School)

  - WBHS Digital marquee @Washington Ave. & Bypass Rd.

  - Local media outreach (newspapers, radio, community calendars)

  - Flyers and posters in local businesses and community centers

  - Consider live streaming the event – live stream can also be shown on the hospitality area’s Active Board!

- Responsible: Communications & Webmaster

- Key Consideration: Designate a point person for all marketing efforts.

Phase 3: Final Preparations & Logistics (2-4 Weeks Prior to BRFB)

Focus shifts to finalizing details, training, and procurement.

- Finalize Volunteer Roster & Create Detailed Schedule:

- Action: Confirm all volunteer positions and create a comprehensive schedule with assigned roles, shift times, and reporting locations using Sign-Up Genius.

- Responsible: Volunteer Coordinator

- Key Considerations:

  - Ensure adequate coverage for all areas throughout the event. Identify backup volunteers.

  - The President, Volunteer Coordinator, and Treasurer will generally act as “Floaters” for the duration of the event and should not be assigned stationary roles. These individuals will check in on all volunteer stations at intervals throughout the event to answer questions, provide resources, or support breaks.

- Conduct Volunteer Training & Briefing Sessions:

- Action: Hold training sessions for volunteers, especially for roles involving cash handling, food safety, or specific procedures (e.g., band check-in). Provide an overview of the event, key contacts, and emergency procedures.

- Responsible: Volunteer Coordinator with support from the Executive Board

- Output: Distribute role-specific instruction sheets.

- Finalize Arrangements with Food/Merchandise Vendors & Concessions Plan:

- Action:

  - Confirm final arrival times, setup needs, power requirements, and any other specific logistics with all external vendors.

  - Finalize the menus, pricing, and create a master purchase list for all supplies needed for Booster-run concessions.

- Responsible: Ways & Means, Volunteer Coordinator, Treasurer

- Key Consideration: Plan for waste management and cleanup for food service areas throughout and after the event.

- Competition Program: Planning, Development & Publication

This section outlines the comprehensive process for creating and distributing the event program, a key informational tool for attendees and an important component of the event experience. While some content gathering begins earlier (e.g., sponsor commitments in Phase 1, judge biographies in Phase 2 ), Phase 3 is when the program itself is fully developed and finalized.

- Action: Lock in the performance schedule based on registered bands. Gather all content for the event program (band list, performance times, judge bios, sponsor ads, thank you messages).

- Action: Finalize Program Content Strategy & Timeline

  - Confirm the final performance schedule based on registered bands; this is a critical input for the program.

  - Establish and communicate a clear timeline for all stages of program development: content submission deadlines, design completion, proofreading periods, and final publication (both print and digital).

- Responsible: Program Coordinator (if designated, otherwise Executive Board lead), Webmaster, Digital Content Coordinator.

- Action: Gather and Consolidate All Program Elements

  - Compile the official list of participating bands and their confirmed performance times.

  - Collect and finalize judge biographies (ensure these were obtained as per Phase 2, Section 3).

  - Incorporate sponsor advertisements and recognition according to agreed-upon levels and benefits (cross-reference with sponsorship forms and commitments from Phase 1, Section 4).

  - Draft and include any necessary thank you messages for volunteers, school administration, staff, and other supporters.

  - Gather any additional desired content, such as a welcome letter from the Director, a brief history of the festival, or special acknowledgments.

- Responsible: Program Coordinator (or Executive Board lead), with support from Sponsorship Coordinator/Ways & Means (for ads) and Director (for welcome letter, specific acknowledgments).

- Action: Program Design & Layout

  - Develop the design and layout for the program. Consider using an established template from previous years for branding consistency, making updates for the current year's specifics.

  - Ensure the design is professional, visually appealing, easy to navigate, and accurately reflects the event's branding (e.g., logos, color schemes).

  - Organize content logically (e.g., schedule of performances, band listings, judge information, sponsor section).

- Responsible: Digital Content Coordinator, Webmaster, or a designated volunteer with graphic design experience.

- Action: Rigorous Proofreading & Final Approval

  - Conduct multiple rounds of thorough proofreading. This should involve several individuals to meticulously check for accuracy in:

  - Band names, classifications, and performance times.

  - Spelling of all names (judges, directors, students if mentioned).

  - Sponsor names, ad content, and recognition levels.

  - All general text, grammar, and punctuation.

  - Obtain final sign-off approval from the Executive Board or a designated senior committee member before any version (print or digital) is published.

- Responsible: A dedicated proofreading team (can include Executive Board members, meticulous volunteers), with final approval by the President or Event Chairperson.

- Action: Publication & Distribution Strategy

  - Coordinate with the Webmaster to prepare and upload the finalized digital version of the program (e.g., PDF format) to the official band website.

  - Ensure the digital file is optimized for various devices (desktops, tablets, smartphones) and is easily downloadable or viewable.

  - Develop and prepare QR codes that link directly to the digital program. These QR codes should be designed for clear printing and strategic placement at various conspicuous locations around the venue (e.g., ticket booths, concession stands, entrances, seating areas) for easy attendee access.

- Responsible: Webmaster, Digital Content Coordinator, Program Coordinator (or Executive Board lead).

- Key Considerations for Program Development:

  - Clear Deadlines: Establish and strictly enforce deadlines for all content submissions (e.g., sponsor artwork, director messages, band information changes) to keep the program on schedule.

  - Sponsor Obligation Fulfillment: Diligently verify that all promised sponsor benefits related to program advertisements (e.g., ad size, color, placement, links in digital version) are accurately delivered.

  - Contingency Planning: Have a brief plan for how to communicate any last-minute critical changes to the schedule if they occur after the program has gone to print (e.g., announcer updates, a small insert, website/social media notification).

- Order/Prepare Trophies & Awards:

- Action: Confirm and order all necessary trophies, plaques, or other awards based on the judging categories and participation levels.

- Responsible: Director

- Key Consideration: Verify all spellings and award details.

- Assemble Visiting Band Information Packets (Final Version):

- Action: Finalize and print/copy all materials for the band packets. Assemble packets for distribution upon band arrival.

- Responsible: Director (with student support)

- Contents: Final schedule, site map, director's letter, meal ticket info (if applicable), local area info, emergency contacts.

- Create Google Drive Folders for Performance Recordings & File Share

- Action: Ensure that each visiting band has a Google Drive folder under the main Booster account. Email links to Band Directors or designees from each school to allow for retrieval of performance recordings after the event.

- Responsible: Director

- Prepare Event Signage:

- Action: Create and print all necessary signage: directional (parking, warm-up, stadium), informational (ticket prices, concessions menu), and recognition (sponsors).

- Responsible: Volunteer Coordinator

- Key Considerations: Ensure signs are clear, professional, and weather-resistant if outdoors.

- Equipment & Supplies Procurement/Check:

- Action: Inventory and ensure all necessary equipment and supplies are available and in working order:

  - Two-way radios for key personnel

  - Recording devices (with batteries)

  - Tables, chairs (school-provided)

  - Tents/Easy-Ups (volunteer-provided)

    - Registration

    - Water stations (2)

    - Band of the Day/Air Grams

    - Main gate/entryway

  - Cash boxes, change, payment processing devices (e.g., Square readers)

  - First aid kit

  - Coolers, water for volunteers/judges

  - Coolers & small water cups for water stations

  - Office supplies (pens, paper, clipboards)

  - Seasonal decorations for hospitality area (may be loaned from front office with advance notice)

  - Active Board for hospitality area. Consider sharing a live stream of the event from the announcer’s booth.

  - Hand stamps for Main Gate

  - Tickets for Ticket Booth and raffle (if applicable)

  - Garbage cans and liners

- Responsible: Volunteer Coordinator

- Key Considerations: Designate a central location for supply distribution and return.

Phase 4: Event Week Mobilization (1 Week to 1 Day Prior to BRFB)

The final push before the event.

- Final Venue Walk-Through:

- Action: Committee leads conduct a thorough walk-through of the venue to confirm logistics, identify any last-minute issues, and visualize event flow.

- Responsible: Vice President, Volunteer Coordinator

- Key Consideration: Areas immediately outside the stadium fence may need to be roped off or cones placed to prevent overnight parking. Ensure entry to and from the stadium is clear for band trailers and large equipment moving routes.

- Confirm Volunteer Shifts & Send Reminders:

- Action: Send out final reminders to all volunteers with their assigned roles, shift times, and role-specific instructions.

- Responsible: Vice President, Volunteer Coordinator

- Key Consideration: Have a plan for no-shows.

- Prepare Cash Boxes & Payment Systems:

- Action: Prepare cash boxes with adequate starting change for ticket sales, concessions, and any merchandise. Test any electronic payment systems.

- Responsible: Treasurer

- Key Consideration: Establish secure procedures for cash handling and collection throughout the event.

- Final Communications:

- Action: Send final confirmation and any last-minute updates to participating band directors, judges, vendors, and key personnel.

- Responsible: Band Director, Ways & Means, Volunteer Coordinator

- Set Up "Day Of" Command Center Plan:

- Action: Designate a central point of contact/location in the cafeteria and away from the main hospitality seating area for event day operations, issue resolution, and communication hub.

- Responsible: Executive Board

- Key Considerations:

  - Set up command center staging area the night before the event.

  - Move all donated food and beverages to the concession stand. Stock coolers so beverages have time to cool overnight.

  - To alleviate confusion and make Day Of distribution of materials go smoothly, set up tables in the Command Center for volunteers to collect items. This will prevent volunteers who are not familiar with the room layout from having to rummage through band cabinets to find what they need.

    - Paper products, plates, utensils, napkins, takeout containers, etc.

    - Cones, straps, blocks & chains for stadium entryways, etc.

    - Signage, poster board, markers, tape, clip boards, printer paper, etc.

  - Designate a box for lost and found items. Utilize a student runner to communicate lost items to the announcer during the event.

Phase 5: BRFB Event Day Execution

This is showtime! Focus on smooth operations and a positive experience for all.

- Early Morning: Setup & Volunteer Check-in:

- Action: Core team arrives for final setup (signage, tables, concessions, command center).

- Action: Volunteer Coordinator manages check-in, provides role-specific briefings, and distributes any necessary equipment (e.g., radios).

- Vendor & Band Arrival/Registration:

- Action: Guide vendors to their designated spots and assist with setup as needed.

- Responsible: Vice President, Ways & Means

- Action: Welcome visiting bands, provide their information packets, direct them to parking and warm-up areas. Collect any outstanding fees.

- Managing Event Flow:

- Action: Ensure the performance schedule runs on time.

- Action: Gate/Ticket Sales: Efficiently manage spectator entry.

- Action: Concessions: Keep lines moving and supplies stocked.

- Action: Band Guides: Assist bands with movement from warm-up to stadium and exit.

- Action: Announcer’s Steward: Ensure all Air Grams and special announcements are delivered to the booth in a timely manner before each band takes the field.

- Action: Judges' Steward: Ensure judges have what they need and that scores are collected efficiently and accurately.

- Hospitality:

- Action: Provide refreshments and a comfortable space for band directors, bus drivers, and judges.

- Troubleshooting & Issue Resolution:

- Action: Designated personnel (e.g., President, Volunteer Coordinator) address any unexpected issues (weather, delays, medical incidents) promptly and calmly. Maintain communication via radios.

- Awards Ceremony:

- Action: Prepare for and execute a timely and organized awards ceremony. Ensure all trophies are correctly presented.

Phase 6: Post-Event Wrap-Up & Review (1 Day to 1 Week After BRFB)

The work continues after the last band leaves.

- Immediate Post-Event: Venue Cleanup & Teardown:

- Action: Coordinate volunteers for thorough cleanup of the stadium, parking lots, and all used facilities. Collect all signage, equipment, and supplies.

- Responsible: Volunteer Coordinator

- Key Consideration: Leave the venue in better condition than it was found, if possible.

- Financial Reconciliation (Next Business Day):

- Action: Treasurer and designated personnel count all cash from sales (tickets, concessions, vendor contributions).

- Action: Prepare and make the bank deposit.

- Action: Compile all receipts for expenses and reconcile against the budget.

- Responsible: Volunteer Coordinator

- Send Performance Recordings to Visiting Band Directors:

- Action: Upload all audio recordings to the Google Drive for distribution to each participating Band Director.

- Key Consideration: This is a valuable service and a good relationship builder.

- Distribute Thank You Communications:

- Action: Send personalized thank you notes/emails to:

  - Sponsors

  - Volunteers (a general thank you blast and specific thanks to key individuals)

  - Participating band directors

  - Judges

  - School administration and staff who provided support

- Key Consideration: Prompt and sincere appreciation goes a long way.

- Celebrate Success & Share Results (Social Media & Community):

- Action: Post a thank you message on social media platforms, highlighting the success of the event, acknowledging participants, sponsors, and volunteers. Share photos/videos (with appropriate permissions).

- Action: Communicate the fundraising results to the Booster membership and school community, emphasizing the impact on the music program.

- Responsible: Webmaster, President, Treasurer, Volunteer Coordinator

- Post-Event Review Meeting & Documentation:

- Action: The BRFB Planning Committee should meet to discuss what went well, what could be improved, and any challenges encountered.

- Output: Document lessons learned, update this Operations Guide with any necessary revisions, and begin preliminary planning/note-taking for the next year's BRFB.

- Key Consideration: Collect feedback from volunteers and Band Directors if possible (e.g., via a simple online survey).

- Final Financial Reporting:

- Action: Treasurer prepares a final financial report for the BRFB, presenting it to the Band Booster membership.