Marching Band

Away Camp

Operations Guide

Contents

Purpose	3

Audience	3

Timeline Overview	3

Phase 1: Pre-Camp Preparations (2-3 Weeks Prior)	4

1.	Host New Parent & Student Away Camp Meeting	4

2.	Assess Needs & Create Sign-Up List	4

Phase 2: Camp Departure, Execution, & Return	7

1.	Donation Drop-Off & Equipment Packing	7

2.	Departure Day Student & Chaperone Check-In	7

Phase 3: Post-Camp Wrap-Up	8

1.	Unpacking & Equipment Return	8

2.	Final Financial Reconciliation	8

3.	Inventory & Debrief	8

Purpose

This guide defines the standardized tasks and responsibilities of the William Byrd Band Boosters in providing logistical, financial, and volunteer support for the annual Marching Band Away Camp. Its aim is to ensure a safe, organized, and successful off-site camp experience for all students and staff.

Audience

This guide is intended for all WBHS Band Booster Board members, committee chairs, chaperones, and volunteers involved in the planning and execution of Away Camp support activities.

Timeline Overview

Phase 1: Pre-Camp Preparations (2-3 Weeks Prior)

Phase 2: Camp Departure, Execution, & Return

Phase 3: Post-Camp Wrap-Up (First Week After Camp)

Phase 1: Pre-Camp Preparations (2-3 Weeks Prior)

This phase focuses on critical parent communication, financial collection, and organizing resources for the off-site trip.

- Host New Parent & Student Away Camp Meeting

- Action: Schedule and conduct a mandatory meeting to explain Away Camp logistics, student expectations, and answer questions. This meeting is the primary opportunity to collect camp fees and all required forms.

- Responsible: Executive Board, Treasurer

- Key Consideration:

  - Emphasize that the Field Trip Permission Slip and Student Health Form are mandatory for travel. No student will be permitted to attend camp without completed forms on file.

  - The medication policy must be clearly explained: All student medications are to be turned in to chaperones upon check-in. Medications must be in the original prescription bottle, clearly marked with the student's name, dosage, and time of day to be taken.

- Assess Needs & Create Sign-Up List

- Action: The Volunteer Coordinator will confer with the Band Director to confirm donation needs. Based on this, they will create or update the master sign-up list for the camp.

- Responsible: Volunteer Coordinator

- Tool: SignUp Genius

- Key Consideration:

  - The list must focus on donations of pre-packaged snacks, cases of water, and electrolyte drink mixes.

  - The list should also include requests for loaned equipment essential for an off-site event, such as large coolers and pop-up canopies.

  - Consult the band’s Corps Commander for information on any planned Band Camp Olympics games that may require supplies, e.g. water balloons, crackers, large tarps.

  - Refer to the previous year's sign-up list for inspiration, but adjust all requested quantities to reflect any increase or decrease in the current year's student headcount.

- Review Traveling Medical Supplies

- Action: A designated board member will conduct a thorough review of the traveling medical bag. All contents must be checked for expiration dates.

- Responsible: Executive Board, Volunteer Coordinator

- Key Consideration: A list of expired or depleted items (e.g., pain relievers, bandages, antiseptic wipes, allergy medication) should be compiled and added to the SignUp Genius donation list to ensure the kit is fully stocked.

- Review & Finalize Student Packing List

- Action: Review the existing student packing list (from the band website/Facebook page) for relevance and update it as needed for the current year's camp location and activities. The finalized list, which must include the mandatory instructions for submitting student medications, is then provided to the Band Director for distribution.

- Responsible: Executive Board, in consultation with the Director

- Key Consideration: The goal is to provide a single, accurate, and comprehensive list to families well in advance to prevent confusion and ensure students arrive fully prepared.

- Distribute Volunteer & Donation Communications

- Action: Distribute the SignUp Genius link across all official channels to ensure maximum reach.

- Responsible: Volunteer Coordinator, Communications & Webmaster

- Key Consideration: The link must be sent to the Band Director for inclusion in official school emails and to the Communications Lead for posting on the band website, Facebook page, and Spond app..

Phase 2: Camp Departure, Execution, & Return

This phase covers the logistics of getting to and from camp, as well as on-site support.

- Donation Drop-Off & Equipment Packing

- Action: Schedule and staff a designated time and location for parents to drop off all donated food, water, and loaned equipment. Volunteers will organize these supplies for efficient transport.

- Responsible: Volunteer Coordinator, General Volunteers

- Key Consideration: All items, especially coolers and canopies, should be clearly labeled with the owner's name to ensure proper return.

- Departure Day Student & Chaperone Check-In

- Action: On the day of departure, designated chaperones will formally check in all attending students. This process includes:

  - A final verification that all fees have been paid and mandatory forms are on file.

  - Collecting all student medications. Chaperones must verify each medication is in its original prescription bottle, clearly labeled with the student's name, dosage, and time of day.

- Responsible: Treasurer, Executive Board, Designated Chaperones

- Key Consideration: This is the final checkpoint. Any student without completed forms or with improperly packaged medication will need to have the issues resolved with their parent/guardian before they are permitted to travel.

- On-Site Chaperone Support

- Action: During camp, Booster chaperones will provide support as directed by the Band Director and staff. This includes managing hydration stations, distributing snacks, assisting with student needs, and administering medications as required.

- Responsible: Designated Chaperones

- Key Consideration: All chaperones are required to schedule and complete a background check with the RCPS Central Office prior to participating in any school event.

Phase 3: Post-Camp Wrap-Up

This phase ensures all camp-related activities are properly concluded upon return.

- Unpacking & Equipment Return

- Action: Upon returning to WBHS, ensure all Booster-related equipment is unloaded. All loaned items (coolers, canopies) and any remaining student medications must be returned to their owners.

- Responsible: Volunteer Coordinator, Chaperones

- Final Financial Reconciliation

- Action: The Treasurer will conduct a final reconciliation of all camp fees, account for any expenses incurred during the trip, and prepare a final financial report for the Booster Board.

- Responsible: Treasurer

- Inventory & Debrief

- Action: Take inventory of any leftover, non-perishable supplies and store them for future band events (e.g. extra snacks can be held for sale at the Blue Ridge Festival of Bands concession stand). The Executive Board and chaperones should hold a brief review of the week to document lessons learned for the next year.

- Responsible:   Volunteer Coordinator, Executive Board

- Output: Updated notes or revisions to this guide based on lessons learned.